# Secondary Framework And Key Approaches

Use the following to plan and timetable your actions and then use it to audit your progress

| Key actions | Overall responsibility for leading | Date planned | Advice/Good practice |
| --- | --- | --- | --- |
| Launch with governors | HT/SPL |  | Use Governor presentation on the website OSOW becomes part of Committee and FGB agendas Governors watch Aimhi Carbon Basics training video |
| Standing item in senior leadership meetings including department meetings | HT/Gov |  | This will ensure sustainability developments remain a high profile, good practice is shared, and progress is regularly reviewed |
| Appoint School Sustainability Leader (SSL) | HT |  | A senior leader within the school who has experience of cross school/ faculty improvement work |
| Appoint OSOW student programme lead (SPL)* | HT/SSL |  | A teacher who would be strong in developing skills in student engagement and cross school programme implementation Full SPL role description in ‘OCOW Guide for senior programme leads’ PPT doc |
| Adopt Student Climate Leader Framework* | HT/SSL/OSOW SPL |  | See separate framework |
| Survey your students, staff, governors, community | SBM/SSL OSOW SPL |  | Use home-school communication system to send out survey link for parent/carers (Accompanying letter explaining OSOW programme and school wish for families to be partners in the programme and sustainability actions) Use 10 mins of staff meeting or support staff meeting for survey. Students to complete surveys online during form tutor time. Surveys will act as baselines of attitudes and leverage in terms of actions i.e. you said in the survey you wanted ….. so we are …… |
| Set up a sustainability working group – head, school sustainability lead, OSOW student programme lead, governor (parent), students, business manager, parent, premises manager etc. Plan dates at first meeting for whole year to ensure strong attendance Standing item for initial year in SLT meetings and department/faculty meetings including updates from sustainability working group | School sustainability lead - SSL |  | Working Group should meet once each term after school. This group will ensure: - surveys and Zero Carbon termly audits are completed - a collaborative vision and moral purpose - priorities from surveys and audits are identified and communicated to all members of school - action planning where all understand roles and responsibilities and strong links with council and local/national organisations are developed - progress of student campaign is monitored - improvements are monitored and evaluated - a strong culture of sustainability is firmly established |
| Launch programme with all staff (all staff must be involved as this is first and foremost a collective endeavour) | SSL/HT |  | Staff meeting/Support staff meeting or part of INSET day This should be inspirational and led by the HT Use the COP26 video to set the context Allow time for talk Share map of journey and emphasize time will be given in staff meetings and INSET days for developments/improvements |
| Training for teaching all staff in climate science basics (all staff must be involved as this is first and foremost a collective endeavour) – Use AimHi training on website and/or Climate Web cards on website | OSOW Student Programme Lead |  | Staff Meeting/Support staff meeting or part of an INSET day Allow time for talk What does it mean for: - me, personally - professionally - for my class - for the school |
| Training for teachers in eco-anxiety – Use Thoughtbox video on website | OSOW Student Programme Lead |  | Vital that teachers understand how to move from issues to hope and how to support resilience and empowerment in their class |
| Create a joint staff/governor sustainability vision for your school | SSL |  | Create draft and then find ways of getting input from: Staff Governors Pupils Families Emphasize this is a collective vision and a collective effort |
| Integrate OSOW into whole school SIP | Leadership Team |  | Sustainability should run through all areas of school life so rather than being a standalone objective it should shape improvements in all areas |
| Sign up to Let’s Go Zero | SSL |  | LGZ will support in all things decarbonisation including providing details of Climate Action Advisors |
| Sign up to National Education Nature Park | SSL |  | The NENP provides a detailed structure for developing school grounds with pupil voice at its heart. It also has an extensive range of resources and links to supportive organisations. |
| Sign up to UKSSN operations group | SBM |  | This operations group provides extensive support and advice for the SBM around school organisation and operations in school particularly in relation to sustainability |
| Launch project to the school community – pupils and families – develop vision further with their voices | SSL/OSOW student programme lead/CL |  | - Try and create an event or day of activities or series of ‘green’ days. Perhaps organise a walk for staff and pupils around the school asking them to ‘dream big’ with green ideas Emphasize: - how OSOW is central to school improvement - how all members of the community are asked to commit to change behaviours and support improvements - share audit priorities and ask for comments - share termly themes - carry out parent skill audit for up-coming term |
| Align school values/learning attitudes with OSOW aims | SSL |  | Sustainability and an understanding of climate change is founded on the strong values/learning attitudes already common in schools e.g. respect, care, togetherness, curiosity, resilience, imagination etc. It should therefore not seem like an add on but more like a practical and relevant enrichment of the learning context. Introduce the idea of Self Care, People Care, Planet Care |
| Audit existing curriculum with departments/faculties against Conceptual Milestones’ document identifying where relevant OSOW curriculum concepts already exist. Agree where gaps will be taught. | OSOW Student Programme Lead/Teachers |  | Staff Meeting X2 Use the OSOW Curriculum Audit Tool OSOW Curriculum Audit Tool.xlsx |
| Assign climate curriculum links responsibility to one person in each department – draw on expertise of Climate/STEM Ambassadors Training in developing climate change within the secondary curricula from UCL | HT/SSL |  | This could also be strengthened through making it part of Performance Management UCL ‘Teaching for sustainable futures’ |
| On a termly basis ‘green’ the remaining curriculum e.g. in Summer Term green Autumn Term Medium Term Planning, in Autumn Term green Spring Term planning etc. See/use examples on website to promote green thinking | OSOW student programme lead/Department climate link teacher |  | Termly staff/department/faculty meeting Over the year, all terms will be greened then the process remains on-going during planning sessions – seeing the curriculum through a green lens |
| Implement/develop tutor group education programme in 6-week blocks across all year groups– See examples on website* Set themes for a three-year cycle | OSOW Student programme lead/CL/Student Climate Ambassadors |  | Link themes to time of year and other significant curriculum themes and/or decarbonisation work. Share themes with hub leader. Network with other schools around themes -sharing ideas and resources Tutor group education on a single theme for a single term e.g. Spring/summer Biodiversity, Summer/Autumn Consumption and Waste etc. Link to - class action/school action - termly Zero Carbon audit (carry out audit for the following term in the preceding term) - family action/pledges - parent/carer skills audit - local organisation support |
| Promote Green Careers | HT/Staff/SSL/HofD |  | Provide opportunities for pupils to make the link between specific skills and specific careers. Also remember research shows environmental activities promote a range of important green skills e, g. collaboration, creativity, problem solving etc. Actively, promote work around green careers during work experience. Green Careers Hub has excellent resources https://www.greencareershub.com/about/ |
| Complete school Zero Carbon audits and develop action plan on a term and a half basis for an individual theme. Use audits alongside CL surveys and research. | HT/SSL/SWG |  | Audit and associated action plan should link to the whole school theme for that term e.g. Biodiversity SSL prepares audit for sustainability working group each term. SSL/OSOWL/CLs ensure it is informed by voices of all members of the community particularly children and young people. SWG decides on key priorities for action plan and ensures it is communicated to all members of the school and leads to a focussed student campaign Sustainability working group ensures action plan also develops much closer partnership with the council and local organisations. |
| Introduce the Count Your Carbon Tool – Establish baseline. Calculate carbon emissions termly to measure and respond to progress towards targets for reduction | SBM |  | # Establish initial baseline and set smart targets. Link to termly focuses and/or whole network targets |
| Ensure SBM/Site Manager and School Sustainability lead attend Climate Action Plan training. Complete Climate Action Plan. Link with Climate Action Advisors. Refer to OSOW network pledges for additional guidance Meets DfE requirements. | HT/SBM/Site Manager/SSL |  | - Let’s Go Zero offer a good range of resources and advice. The Climate Action Plan should be a summary of the actions you have planned against this framework against 4 key areas: - decarbonisation, for example calculating and taking actions to reduce carbon emissions, such as becoming more energy efficient - adaptation and resilience, such as taking actions to reduce the risk of flooding and overheating - biodiversity, for example engaging with the National Education Nature Park # climate education and green careers, such as ensuring the education you provide gives knowledge-rich and comprehensive teaching about climate change, and that your teaching staff and lecturers feel supported to offer this. This aim is comprehensively covered by involvement in the OSOW programme |
| Audit the expertise of your school community and link to planned actions/curriculum modules | OSOW student programme lead |  | # Term and a half audit of parent/carer and staff skills linked to whole school theme so focussed effective support/expertise is offered |
| Plan for local organisation/community/business engagement | OSOW student programme lead |  | Local organisations should be closely linked with school actions/assemblies/tutor groups and class talks. # Children need to see changemakers regularly Use of climate ambassadors |
| Establish termly plan for pupil/family sustainable pledges and actions | Whole staff |  | Each theme should include actions engaging all members of the community in behaviour change and positive action Emphasize the collective impact. Use school communication software to gather data from pledges |
| Establish termly plan for staff/gov sustainable pledges and actions | SSL/OSOW student programme lead/Staff/Gov |  | # Each termly theme should involve changes in staff and governor behaviour. This is about all members of the community committing to change. |
| Network with other schools on curriculum and initiatives and share expertise and resources Link classes within and across schools | OSOW Programme Lead/teachers |  | The wealth of expertise and resources across the OSOW community cannot be underestimated # Children need to feel empowered/inspired through seeing changemakers in other schools This can be done with video link up or in person meeting |
| Audit school grounds and identify opportunities for enhancing biodiversity and promoting outdoor learning | SSL/CL/CAs/Site Manager/SWG |  | # Use the materials from the National Education Nature Park and the OSOW audit |
| Significant focus on school commitment to sustainability on school website | SBM/SSL |  | # Many parents/carers are now choosing their schools with commitment to sustainability and environmental education as a key criterion |
| Regular feature/update/slot in school newsletter/school TV | SSL |  | # The more communication there is the more people can see how they can get involved and the impact the community is having |
| OSOW notice board in prominent place | SSL |  | # See above |
| Create a schedule of green events during the year e.g. Switch Off Fortnight, World Ocean Day, Go Wild in June and schedule resource saving events for the whole year e.g. Business Enterprise, Freegle, Book Swap, Clothes Swap, Toy Swap | SSL |  | This will enable the widening and deepening of the school sustainability culture |
| Give a green context to some of the annual special weeks e.g. Arts Week, Enrichment Week | SSL/HofD |  | # E.g. Book week focuses on environmental texts or Art Week has a nature focus etc. |
| Make carbon literacy training film available to families https://www.youtube.com/watch?v=HExapQfulPg | SSL |  | # Use The Great Big Lesson for Climate and Nature: Live from COP26 |
| Pilot assessment of impact in some key areas See resources on school website | SSL |  | Sampling of diverse groups of children for conferencing to explore how best to evaluate impact of class learning, assemblies, initiatives etc. |
| Write formal assessment guidelines See policy on website | SSL |  | From what you have learned develop policy |
| OSOW student programme lead attends termly OSOW meetings | OSOW Student Programme Lead |  | Ensures on-going professional development, networking and information/funding updates |
| Analyse procurement choices and adopt sustainable procurement approaches guidelines. | SBM |  | SBM training will provide a clear approach. Encourage SBM to liaise with other SBMs to share good providers/products. UKSSN provides policy examples |
| Plan for comprehensive and systematic approach to nature connection and outdoor learning. | Whole staff |  | Timetabling of nature connection opportunities Training in outdoor learning/Beach School/Forest School Putting outdoor learning directly into plans |
| Create induction pack for new staff | SSL |  | Include access to Carbon Literacy Video Training/Eco-Anxiety Video Training/ OSOW website. Prior to starting ensure training is completed |
| Include sustainability element/question when interviewing for all new staff | HT |  | E.g. How would you integrate learning about sustainability into the curriculum? |
| Sustainability as performance management target for all staff /curriculum leads / head | HT/Govs |  | # Using present school improvement systems ensures this is not an add-on for staff rather supported professional improvement. It also ensures regular reviews. For curriculum leads it is about facilitating the greening of their curriculum as well as resourcing their subject in a sustainable manner. |
| Include OSOW in school presentations to new parents | HT |  | Make parents/carers see learning about sustainability and climate change is a core element of your class and wider curriculum |
| Calculate end of year carbon emissions and compare with other schools. Introduce the ‘Playground’ element into lessons | SBM/Site Manager/Staff |  | Benchmarking aids evaluation. ‘Playground’ encourages deeper, practical understanding for children |
| Link nationally with other schools and organisations on sustainability initiativesLink nationally with other schools and organisations on sustainability initiatives | Staff/SSL |  | Make the collective power of change evident |
| Establish a systematic annual programme of assessment/evaluation | Gov/SSL/Assessment lead |  | On a termly basis, Senior Project Lead conferences children against the conceptual milestones and skills based on their curriculum, assembly learning and actions from that term. Findings inform future planning. Parental attitudes and behaviour changes are evaluated twice yearly |
| Review and develop Climate Action Plan further | HT/SBM/Site Manager/Gov/SSL |  | The action plan should be seen as a fluid document responding to change in the school, locally and nationally |
| Link internationally with other schools and organisations on sustainability initiatives | Staff/SSL |  | Make the collective power of change evident |
| Completion of a Net Zero Route Map outlining broad measures the school will take to reach Net Zero by 2030 | Gov/HT/SBM/Site Manager/Council |  | Work with the council for structure and advice |
| School Grounds – develop a 3-year nature recovery plan for the whole school site identifying opportunities to increase biodiversity | SBM/Site Manager |  | Work with Environmental Education Officer and local organisations |
| Include reference to UN Sustainable Development Goals in lesson planning | HofD/Department Climate link teacher |  | Applicable for upper KS3/4 and above |
| School business manager to attend regular network meetings to look at issues/good practice around sustainability | SBM |  | Vital for on-going, up-to-date support |

Add acronym key, e.g.

HT	Head teacher

SPL	Senior programme lead